## Test Plan
TEST PLAN — SauceDemo E-Commerce Application
1. OBJECTIVE
Purpose | Validate the functional behaviour of the SauceDemo e-commerce web application to ensure all core user flows work correctly across supported browsers.
2. SCOPE
In Scope | • Login / Logout • Product listing & sorting • Add / Remove product from cart • Checkout flow (customer details, order summary, confirmation) • Error messages for invalid inputs
Out of Scope | • Payment gateway integration • Performance / load testing • Mobile native app testing • Admin panel
3. TEST APPROACH
Testing Types | • Manual functional testing • Automation testing (Playwright + TypeScript) • API testing (Postman — ReqRes.in)
Test Design Technique | • Equivalence Partitioning • Boundary Value Analysis • Exploratory Testing
4. TEST ENVIRONMENT
Application URL | https://www.saucedemo.com
Browsers | Google Chrome (latest), Mozilla Firefox (latest), Microsoft Edge (latest)
Operating System | Windows 11
Tools | VS Code, Playwright, Postman, GitHub
5. TEST CREDENTIALS
Valid Username | standard_user
Valid Password | secret_sauce
Locked User | locked_out_user
Problem User | problem_user
6. ENTRY CRITERIA
Entry Criteria | • Application is accessible via browser • Test cases are reviewed and approved • Test environment is set up and stable
7. EXIT CRITERIA
Exit Criteria | • All planned test cases are executed • All critical and high severity bugs are resolved • Test summary report is prepared
8. RISKS & MITIGATION
Risk 1 | Demo site may be down → Mitigation: Test during off-peak hours
Risk 2 | Selector changes in UI → Mitigation: Use stable data-test attributes
Risk 3 | Browser compatibility issues → Mitigation: Test on Chrome, Firefox, Edge
9. DELIVERABLES
Documents | • test-plan.xlsx • test-cases.xlsx • bug-report.xlsx • RTM.xlsx • Postman Collection (JSON) • Playwright Automation Scripts (GitHub)
10. PROJECT TIMELINE
Month 1 — Manual Testing | Test plan, test cases, bug reports, RTM
Month 2 — API Testing | Postman collection, API test report
Month 3 — Automation | Playwright scripts, POM structure, GitHub push, README
11. PREPARED BY
Tester Name | Sevner
Project | QA Portfolio — E-Commerce Testing
Version | v1.0

## Revision History
REVISION HISTORY
Version | Date | Description | Author
v1.0 | 2026-07-11 | Initial Test Plan created | Sevner